Agile Delivery Cheat Sheet

How to Read & Interpret Each KPI Metric

1. Delivery KPIs  ─  Measure the speed and scope of deliverables at sprint and release level

These metrics reveal whether your team is consistently delivering on its commitments. Use them to surface gaps between plan and reality early, before they compound.

| Metric | Formula | How to Read It | Healthy Sign | Warning Sign |
| --- | --- | --- | --- | --- |
| Scope Achievement Rate | Completed Scope / Planned Scope × 100 | Shows what percentage of planned features were completed in a sprint. Closer to 100% indicates stronger estimation accuracy and execution. If consistently below 80%, revisit estimation and prioritization processes. | Stable at 90–100% across sprints | Repeatedly drops below 70% |
| Release Cadence | Total Time / Number of Releases | Measures delivery frequency. Smaller values mean higher-frequency releases. Widening intervals delay market feedback and let risk accumulate. Target: within one sprint cycle. | Interval is shrinking over time | Intervals widening or becoming irregular |
| Innovation Lead Time | Feedback Date − Idea Proposal Date | Speed from idea to user-validated feedback. Shorter means faster hypothesis-testing cycles. Long lead times often point to excessive WIP or slow approval gates. | Consistently decreasing trend | No change over months |
| Task Turnaround Time | Completion Timestamp − Assignment Timestamp | Processing speed of individual tasks. Track both mean and variance. High variance signals dependencies or idle waiting between handoffs. | Low mean with low variance | Frequent outlier tasks appearing |

2. Flow KPIs  ─  Measure the efficiency and stability of work in motion

Grounded in Lean and Kanban thinking, these metrics make bottlenecks and waste (waiting, rework, excessive WIP) visible — giving you a clear starting point for continuous improvement.

| Metric | Formula | How to Read It | Healthy Sign | Warning Sign |
| --- | --- | --- | --- | --- |
| Velocity Stability | Standard Deviation of Sprint Velocity | Lower values mean more predictable output. Instability points to scope changes, team absences, or technical debt. Stabilize first, then improve the average — order matters. | Std dev within 20% of velocity mean | Large swings every sprint |
| Work Item Flow (Throughput) | Completed Items per Day | Throughput at a stable WIP level. By Little's Law: Lead Time = WIP / Throughput — so raising throughput or reducing WIP directly shortens lead time. | Stable or improving throughput | Sudden drops or spikes |
| Value Flow Ratio | Value-Add Time / Total Flow Time × 100 | Proportion of time spent on genuinely value-creating work. Low ratios indicate waste: waiting, rework, excessive meetings. Lean practice targets 50%+. | Above 50% and rising | Below 30% or on a downward trend |
| Parallel Work Load (WIP) | Number of Active Items at a Given Point | Too many simultaneous tasks increase context-switching and reduce throughput. In Kanban, enforce WIP limits. Set appropriate limits based on team size. | Stays within WIP limits consistently | WIP limit breaches normalized |

3. Quality KPIs  ─  Measure software quality and test coverage maturity

Building fast is only half the equation. These metrics ensure you're also building things that don't break. Track automation rate and defect density together to see the full quality picture.

| Metric | Formula | How to Read It | Healthy Sign | Warning Sign |
| --- | --- | --- | --- | --- |
| Regression Test Automation Rate | Automated Regression Tests / Total Regression Tests × 100 | Higher means faster releases and fewer human errors. If the rate drops with each new feature, test debt is accumulating and needs dedicated payback sprints. | Above 80% and growing | Drops sharply after new feature additions |
| Production Defect Frequency | Reported Bugs / Number of Releases | Proxy for release quality. High values suggest inadequate test coverage or unclear requirements. Combine with defect categorization (severity, area) to find root causes. | Declining trend release over release | Same area failing repeatedly |
| Release Defect Density | Defect Count / KLOC (per 1,000 lines of code) | Code quality density. Industry average is 1–25 defects/KLOC, but your own trend matters more. Check whether refactoring or static analysis adoption is driving improvement. | Continuously decreasing | Concentrated in specific modules |
| Deploy Reliability Index | Incident-Free Deploys / Total Deploys × 100 | Deployment success rate — reflects CI/CD maturity and infrastructure stability. Combine with MTTR (Mean Time to Recovery) when incidents do occur. | Maintained above 95% | Rollbacks on every deploy |

4. Planning KPIs  ─  Measure forecast accuracy and backlog management maturity

Use these metrics to develop a team that can plan reliably and execute predictably. Analyze spillover and forecast bias to improve refinement and estimation processes over time.

| Metric | Formula | How to Read It | Healthy Sign | Warning Sign |
| --- | --- | --- | --- | --- |
| Backlog Readiness Index | Ready Items / Total Backlog Items × 100 | Percentage of items that are implementation-ready at sprint start. Low scores mean refinement is insufficient, forcing spec clarification mid-sprint. Target: 80%+ of next sprint ready at all times. | 80%+ of next sprint items ready | Spec changes spike after sprint start |
| Sprint Spillover Rate | Carried-Over Stories / Sprint Stories × 100 | Work that didn't finish and rolled into the next sprint. High values signal estimation issues or mid-sprint interruptions. Log spillover item types to identify root causes. | Consistently within 5–10% | 20%+ spillover every sprint |
| Forecast Accuracy | (Forecast − Actual) / Forecast × 100 | How closely work completion matches the plan. ±20% is the target. Track both over- and under-estimation separately — a consistent directional bias is a system problem to fix. | Stable within ±20% | Bias consistently in one direction |
| Planned vs. Delivered Scope | Delivered Features / Planned Features × 100 | Feature-level delivery ratio. Unlike story-point velocity, this is a stakeholder-facing trust metric. Reflects the team's credibility in keeping commitments. | Stable at 90%+ | Persistent gap vs. stakeholder expectations |

5. Team Health KPIs  ─  Measure team vitality, morale, and collaboration

Quantitative metrics alone miss the human dimension. These indicators complement the numbers, helping sustain long-term performance. Focus on trends and inflection points, not just raw scores.

| Metric | Formula | How to Read It | Healthy Sign | Warning Sign |
| --- | --- | --- | --- | --- |
| Engagement Rate | Actively Contributing Members / Total Members × 100 | Degree of active participation. If declining, conduct 1-on-1s to assess psychological safety. Go beyond attendance — measure frequency of contributions and proposals. | Stable above 80% | Gradual decline month over month |
| Incident Resolution Time (MTTR) | Time from Detection to Resolution | Incident response agility. Shorter times reflect mature on-call processes and runbooks. Pair with MTBF to decide whether to invest in prevention or faster recovery. | Resolved within SLO and shrinking | Same incident types recurring and dragging on |
| Goal Achievement Rate | Goals Achieved / Goals Set × 100 | Sprint goal completion rate. Link to OKRs/KRs to verify strategic alignment. A consistent 100% may mean goals are too easy — consider stretch targets where 60–70% achievement is expected. | Stable in the 70–90% range | 0% or always 100% (goal-setting may be off) |
| Mood Index | Average Mood Score (e.g., 1–5 scale) | Aggregated team sentiment per sprint, typically gathered in retrospectives. Focus on trend and inflection points over the raw score. A sudden drop signals an event worth investigating. | Consistently high with active retro discussion | Sharp drop, or everyone scores 'neutral' with no discussion |

Tip: No single metric tells the whole story. Read multiple KPIs together for an accurate picture of your team's health. Prioritize trends and change points over absolute values.